🇮🇳 VISHWAKARMA PLATFORM India Self-Hosting & Dependency Migration Plan Eliminating reliance on foreign compute and third-party managed services April 2026 ¦ Deepak Chary ¦ CONFIDENTIAL

# 1. Executive Summary

The Vishwakarma platform currently operates across a patchwork of third-party managed services based predominantly outside India — Cloudflare (US), Vercel (US), Supabase (US), Groq (US), and Oracle Cloud (global). While this enabled rapid development, it creates strategic vulnerabilities: data sovereignty risk, unpredictable foreign-currency costs, vendor lock-in, and latency penalties for Indian users.

This plan defines a phased, systematic migration from external dependencies to self-managed, India-resident infrastructure. The goal is not to eliminate cloud entirely, but to own the critical compute layer — keeping only truly global edge/CDN functions on Cloudflare while running all stateful, AI, and data workloads on hardware or VMs physically hosted in India.

| GOAL | By end of Phase 3 (target: Q4 2026), 90%+ of platform compute, data, and AI inference runs on India-resident infrastructure under Deepak's direct operational control — with zero Supabase dependency, zero Vercel dependency, and self-hosted LLM inference replacing paid API calls. |
| --- | --- |

# 2. Current Dependency Map

The table below maps every Vishwakarma service against its current external dependency, associated risk, and data residency.

| Service | Current Platform | Dependency Type | Data Residency | Risk Level |
| --- | --- | --- | --- | --- |
| narad (AI Workspace) | Cloudflare Pages | Compute + Edge routing | US/Global | 🟡 Medium |
| narad — LLM inference | Groq / Anthropic / OpenAI | AI API (paid, rate-limited) | US | 🔴 High |
| narad — Brain storage | Supabase (hosted) | Managed Postgres + pgvector | US | 🔴 High |
| narad — Knowledge graph | Neo4j (self-hosted OCI) | Graph DB on foreign VM | OCI region | 🟡 Medium |
| vishwakarma (Provisioning) | Cloudflare Workers | Serverless compute | US/Global edge | 🟡 Medium |
| vishwakarma — Auth | Supabase Auth (hosted) | Managed Auth + JWT | US | 🔴 High |
| chitragupta (Finance) | Cloudflare Workers | Serverless compute | US/Global edge | 🟡 Medium |
| karma (Compute Marketplace) | OCI VM + Docker | VM on foreign cloud | OCI region | 🟡 Medium |
| kanak (Landing Page) | Cloudflare Pages | Static hosting (CDN) | Global edge | 🟢 Low |
| unnati (Dashboard) | Vercel | Managed Next.js hosting | US | 🔴 High |
| indra (Automation) | Docker on OCI VM | n8n on foreign cloud VM | OCI region | 🟡 Medium |
| Monitoring — Metrics | Prometheus + Grafana (OCI) | Observability on foreign VM | OCI region | 🟡 Medium |
| Monitoring — Logs | Loki + Promtail (OCI) | Log aggregation on foreign VM | OCI region | 🟡 Medium |
| Infrastructure state | Terraform Cloud (HashiCorp) | Managed state + CI/CD | US | 🟡 Medium |

| WHY THIS MATTERS | Indian data protection law (DPDP Act 2023) and RBI/SEBI mandates for financial data require personal and financial data to be stored in India. Supabase's US-hosted Postgres and Vercel's US edge functions both place Indian user data outside Indian jurisdiction — a compliance risk as the platform scales. |
| --- | --- |

# 3. Target Architecture — India-Resident Stack

The target state routes all stateful, sensitive, and compute-intensive workloads to India-resident infrastructure. Cloudflare is retained only for global CDN/edge routing — a stateless, non-data-holding role that carries no sovereignty risk.

## 3.1  Compute Layer

| Layer | Current | Target (India) | Notes |
| --- | --- | --- | --- |
| Primary Compute | OCI VM (global region) | Dedicated server / Hetzner India / AWS ap-south-1 | Prefer bare metal or dedicated VM in Mumbai/Chennai |
| Kubernetes Orchestration | K3s on OCI VM | K3s on India-resident VM | Migrate existing K3s modules via Terraform |
| Serverless Workers | Cloudflare Workers | Retain CF Workers for stateless API proxy only | Workers hold no data; low sovereignty risk |
| Static Hosting | Cloudflare Pages / Vercel | CF Pages (stateless CDN) — Vercel fully removed | unnati migrates to self-hosted Next.js on India VM |
| Container Registry | Docker Hub (public) | Self-hosted Harbor or GitHub Packages | Avoid pulling from Docker Hub in prod |

## 3.2  Data Layer

| Data Store | Current | Target (India) | Migration Effort |
| --- | --- | --- | --- |
| Primary Database | Supabase managed Postgres | Self-hosted Postgres (Docker / K3s) on India VM | High — schema export + Row Level Security re-implementation |
| Auth System | Supabase Auth (hosted) | Keycloak or Supabase self-hosted on India VM | High — all client JWT issuers must change |
| Vector Search | pgvector via Supabase | pgvector extension on self-hosted Postgres | Low — same extension, new host |
| Graph Database | Neo4j on OCI VM | Neo4j on India-resident VM | Low — container migration |
| Workflow State | n8n on OCI (indra) | n8n on India VM (same Docker Compose) | Low — volume migration |
| Secrets / Env | .env files + CF secrets | HashiCorp Vault (self-hosted) or Infisical | Medium — re-wire all service env injection |
| Terraform State | Terraform Cloud | Self-hosted Terraform state (S3-compatible store) | Medium — state migration + CI/CD update |
| Object Storage | None currently | MinIO on India VM (S3-compatible) | New capability — needed for file uploads |

## 3.3  AI Inference Layer

This is the highest-cost and highest-dependency area. The platform currently pays per-token to US providers (Groq, Anthropic, OpenAI). The target is to run open-weight models on India-resident GPU compute for the majority of inference workload, with external APIs as a premium fallback only.

| Use Case | Current Provider | Self-Hosted Alternative | Recommended Model |
| --- | --- | --- | --- |
| General chat / narad | Groq (LLaMA 3) | Ollama on India GPU VM | LLaMA 3.1 8B / Mistral 7B |
| Code generation | Anthropic Claude | Ollama + CodeLLaMA or DeepSeek Coder | DeepSeek Coder 6.7B |
| Embeddings (pgvector) | OpenAI text-embedding-3 | Nomic-embed or all-MiniLM (local) | nomic-embed-text |
| Long-context / complex tasks | Anthropic Claude API | Retain as paid premium fallback | Claude Sonnet (API) |
| Image / multimodal | Not currently used | LLaVA or Gemma3 multimodal on GPU VM | LLaVA 1.6 |

| GPU REQUIREMENT | Running LLaMA 3.1 8B at full speed requires a GPU with at least 12GB VRAM (e.g. RTX 3060 12GB, RTX 4060, or A4000). For 70B models, a multi-GPU setup or a cloud instance in ap-south-1 (AWS g4dn / g5) is needed. Initial migration can use quantised (GGUF Q4) models on CPU for testing before GPU procurement. |
| --- | --- |

# 4. Phased Migration Plan

Migration is structured in three phases. Each phase can be executed independently and builds on the previous. No phase requires a full platform downtime — services are migrated one by one with dual-run validation periods.

Phase 1 — Foundation: India-Resident Compute (Weeks 1–4)

### Objective

Provision a reliable, India-hosted primary compute node and migrate stateless workloads first, establishing the base infrastructure before touching databases or auth.

### Step 1.1 — Provision India VM / Bare Metal

- Option A (Recommended): Hetzner Cloud — AX41 Dedicated Server (India PoP via partner) or CX31/CX41 in Ashburn for now, with migration to Hetzner's planned India DC

- Option B: AWS EC2 ap-south-1 (Mumbai) — t3.xlarge (4 vCPU, 16GB RAM) ~$120/mo, or Reserved Instance for ~$60/mo

- Option C: Azure India Central (Pune) — B4ms or D4s_v3 instance

- Option D: Physical mini-server at home / colocation in Hyderabad — most cost-effective long term (see Section 6)

### Step 1.2 — Bootstrap Server with Existing Ansible / Setup Script

- Reuse the existing vm-setup.sh (referenced in Znext/02_vm-migration-plan.md)

- Install: Docker, Docker Compose, K3s, Prometheus, Grafana, Loki, Promtail, Neo4j

- Configure firewall (ufw), SSH hardening, fail2ban, automatic security updates

- Set up Wireguard VPN or Tailscale for secure dev access

### Step 1.3 — Migrate karma (Compute Marketplace) — First

- karma already runs on Docker/FastAPI — lowest risk migration

- Export OCI VM volumes → rsync to India VM

- Update karma's DNS / CF Worker proxy to point to India VM IP

- Validate: API endpoints, encryption, Prometheus metrics, Loki logging

### Step 1.4 — Migrate indra (n8n Automation)

- Stop n8n on OCI, tar the n8n data volume, rsync to India VM

- Start n8n on India VM with same Docker Compose config

- Update all webhook URLs in workflows to new IP/domain

- Validate all active workflows fire correctly

| Duration | 2–4 weeks |
| --- | --- |
| Risk level | Low — karma and indra are stateful but not user-auth critical |
| Rollback plan | Keep OCI VMs running in parallel for 2 weeks post-migration |
| Success metric | karma and indra fully operational on India VM, OCI VMs decommissioned |

Phase 2 — Data Sovereignty: Database & Auth Migration (Weeks 5–10)

### Objective

Move all stateful data — Postgres, Auth, pgvector — off Supabase's US-hosted managed service onto the India VM. This is the highest-effort and highest-impact phase.

### Step 2.1 — Self-Host Supabase (Preferred) or Switch to Postgres + Keycloak

- Option A — Supabase Self-Hosted: Supabase provides an official Docker Compose self-host stack (Kong, GoTrue, PostgREST, Realtime, Storage). Deploy on India VM and retain the same Supabase client SDK — minimal code changes.

- Deploy via: github.com/supabase/supabase (docker/docker-compose.yml)

- All existing RLS policies, schemas, and Edge Functions remain compatible

- Option B — Postgres + Keycloak: Heavier migration but vendor-neutral. Replace Supabase Auth with Keycloak (OIDC/SAML provider), replace PostgREST with direct Drizzle/Prisma ORM calls.

- Recommendation: Start with Option A (self-hosted Supabase) — it preserves existing code, accelerates timeline, and is still India-resident.

### Step 2.2 — Database Migration

- Export Supabase hosted Postgres: pg_dump --schema=app_data (and public)

- Restore to self-hosted Postgres on India VM: pg_restore

- Migrate pgvector extension and all vector embeddings

- Update all SUPABASE_URL env vars across narad, vishwakarma, chitragupta, kanak, unnati

- Run dual-write validation period: 3–5 days with both DBs receiving writes, compare checksums

### Step 2.3 — Auth Migration

- Self-hosted Supabase GoTrue handles auth — same JWT format, same API surface

- Issue: existing Supabase-issued JWTs will expire; no force-logout needed if JWT_SECRET matches

- Update SUPABASE_ANON_KEY and SUPABASE_SERVICE_KEY in all services to point to India instance

- Test: login, register, password reset flows on kanak, unnati, vishwakarma

### Step 2.4 — Migrate unnati off Vercel

- unnati is a Next.js app — run it with: docker run -p 3000:3000 unnati-next

- Build: docker build -t unnati-next . inside the unnati directory

- Deploy container on India VM behind Nginx reverse proxy

- Point DNS / CF Worker proxy to India VM for unnati subdomain

- Vercel project can be deleted after 1-week validation

| Duration | 4–6 weeks (database migration must not be rushed) |
| --- | --- |
| Risk level | High — auth and database are platform-critical; requires careful dual-run |
| Rollback plan | Supabase hosted remains fully intact; rollback = flip DNS and env vars |
| Success metric | All 6 services authenticated via India-hosted Supabase, Vercel decommissioned |

Phase 3 — AI Sovereignty: Self-Hosted LLM Inference (Weeks 8–14)

### Objective

Replace paid LLM API calls (Groq, OpenAI, Anthropic) for routine inference with self-hosted open-weight models running on India-resident GPU compute. Retain paid APIs only for tasks genuinely requiring frontier-model capability.

### Step 3.1 — Deploy Ollama on India GPU VM

- Install Ollama on the India compute node (requires CUDA/ROCm drivers if GPU available)

- Pull initial models: ollama pull llama3.1:8b, ollama pull nomic-embed-text

- Expose Ollama API internally (no public exposure — accessed only by narad worker)

- Update narad's LLM provider configuration to use Ollama as primary, Groq as fallback

### Step 3.2 — Replace Embeddings (pgvector brain storage)

- Current: OpenAI text-embedding-3-small API call per memory write/search

- Replace: POST to http://india-vm:11434/api/embeddings with model=nomic-embed-text

- Re-embed existing knowledge graph entries using the new local model

- Validate: semantic search quality on narad brain queries

### Step 3.3 — Hardware Procurement Plan (India)

For serious inference workload, dedicated GPU hardware is the most cost-effective long-term solution. Options ranked by cost/performance:

| Option | Hardware | Est. Cost | LLM Capability | Recommended For |
| --- | --- | --- | --- | --- |
| Entry | RTX 3060 12GB (used) + workstation | ₹45,000–65,000 | LLaMA 3.1 8B Q4, Mistral 7B | Dev + light prod traffic |
| Mid | RTX 4070 Ti 12GB + mini-ITX build | ₹90,000–1,10,000 | LLaMA 3.1 8B full, 13B Q4 | Small prod traffic |
| Production | RTX 4090 24GB or 2× RTX 3090 | ₹1,60,000–2,40,000 | LLaMA 3.1 70B Q4 | Full prod + marketplace |
| Cloud GPU | AWS g4dn.xlarge ap-south-1 (T4 16GB) | ~$0.53/hr (~₹44/hr) | LLaMA 13B, Mistral 7B | Burst / before hardware |
| Cloud GPU | Lambda Labs A10 (24GB) on demand | ~$0.60/hr | LLaMA 70B Q4 | Heavy inference bursts |

| RECOMMENDATION | Start Phase 3 with AWS g4dn.xlarge in ap-south-1 (Mumbai) — no hardware procurement, immediate GPU access, India-resident. Once traffic patterns are understood, procure an RTX 4070 Ti home server for base load and use cloud GPU for bursts. This hybrid cuts inference costs by 70-80% vs. paying Groq/OpenAI per token. |
| --- | --- |

| Duration | 4–6 weeks (hardware procurement adds variable lead time) |
| --- | --- |
| Risk level | Medium — AI quality regression possible; A/B testing required |
| Rollback plan | Groq/OpenAI API keys remain valid; flip provider in narad config |
| Success metric | >80% of narad inference requests served by local Ollama, API spend reduced by 70%+ |

# 5. Target Infrastructure Topology

After all three phases are complete, the Vishwakarma platform will operate across two tiers: a global stateless edge (Cloudflare) and an India-resident stateful core (self-managed).

## 5.1  Network Layout

| Global Edge (Cloudflare) | CDN + static asset delivery for kanak, narad frontend. CF Workers act as stateless API proxy/router only. No data stored at edge. |
| --- | --- |
| India Primary VM | All application services: karma (FastAPI), indra (n8n), unnati (Next.js), vishwakarma API backend. K3s orchestration. Reverse proxy: Caddy or Nginx. |
| India Data VM (or same VM) | Supabase self-hosted stack (Postgres 15 + pgvector + GoTrue + PostgREST + Realtime). Neo4j graph database. MinIO object storage. Redis queue (for karma). |
| India AI Inference VM / GPU | Ollama server. Self-hosted LLM models (LLaMA, Mistral, CodeLLaMA, Nomic-embed). Internal network only — not exposed publicly. |
| Monitoring (same India VM) | Prometheus, Grafana, Loki, Promtail, Alertmanager. Dashboards accessible via VPN/Tailscale. |
| Secrets Management | HashiCorp Vault or Infisical self-hosted on India VM. Replaces .env files and Cloudflare secret management. |
| Terraform State | MinIO bucket on India VM (S3-compatible backend) replaces Terraform Cloud. |
| VPN / Access | Tailscale mesh VPN for secure access between all nodes and developer machines. No public SSH exposure. |

## 5.2  DNS & Routing Strategy

- Primary domain (e.g. vishwakarma.in or similar): Cloudflare DNS with proxying enabled

- kanak.*, narad.*: Point to Cloudflare Pages (static) — no change needed

- api.*, app.*, dashboard.*: CF DNS → CF Worker → India VM reverse proxy (Caddy/Nginx)

- Internal services (Grafana, Vault, Loki): accessible only via Tailscale — never public

- Supabase endpoint: internal URL (india-vm:8000) — CF Worker injects auth header as proxy

# 6. Home Server / Colocation Option (Hyderabad)

The most cost-effective long-term option is a self-owned server hosted at home in Hyderabad or colocated at a Hyderabad DC. This eliminates all recurring VM costs and gives full hardware control.

## 6.1  Recommended Home Server Build

| Component | Recommended Part | Approx. Cost (INR) | Notes |
| --- | --- | --- | --- |
| CPU | AMD Ryzen 9 5900X (12-core) or 7900X | ₹28,000–45,000 | Strong single-thread + multi-thread for K3s + FastAPI |
| RAM | 64GB DDR4/DDR5 ECC (or non-ECC) | ₹15,000–22,000 | Minimum 32GB; 64GB for comfortable K3s + LLM |
| GPU | RTX 4070 Ti 12GB (new) or RTX 3090 24GB (used) | ₹55,000–95,000 | 3090 24GB preferred for larger LLM models |
| NVMe SSD | 2TB Samsung 990 Pro or WD Black SN850X | ₹14,000–18,000 | OS + Docker volumes + DB storage |
| HDD | 8TB Seagate IronWolf NAS | ₹14,000–16,000 | Backups, media, log archives |
| Motherboard | ASUS ProArt B650-Creator or MSI MEG X570 | ₹18,000–28,000 | Good PCIe lanes, IPMI on some |
| PSU | 850W 80+ Gold Seasonic or Corsair | ₹10,000–14,000 | GPU headroom essential |
| Case | Fractal Define R5 / Meshify C | ₹8,000–12,000 | Good airflow for 24x7 operation |
| UPS | APC 1500VA / Luminous 1500VA | ₹12,000–18,000 | Essential for Hyderabad power fluctuations |
| Total Estimate |  | ₹1,74,000–2,68,000 | One-time capital cost; ~18–24 month cloud ROI breakeven |

## 6.2  Connectivity Requirements

- Minimum: 100 Mbps symmetric fiber (Airtel/Jio Business preferred over residential)

- Recommended: 200–500 Mbps symmetric + static IP (additional ~₹500–1000/month)

- Backup: 4G/5G LTE router (Jio/Airtel) for failover on residential power/link outages

- DDNS: Use Cloudflare API to update DNS automatically on dynamic IP (if static IP not available)

## 6.3  Colocation Alternative (Hyderabad)

- Ctrl S Datacenters, Hyderabad — Tier III, LEED Platinum certified, TRAI licensed

- NxtGen Datacenter, Hyderabad — Carrier-neutral, multiple ISP options

- Reliance IDC / STT GDC Hyderabad — Large enterprise-grade facilities

- Typical colocation cost: 1U–2U rack space = ₹3,000–8,000/month including 10–20 Mbps guaranteed, with burst to 100 Mbps

- Advantage: Professional power conditioning, diesel UPS, redundant cooling, physical security — eliminates home power risks

# 7. Cost Analysis: Current vs. Target

## 7.1  Current Monthly Spend (Estimated)

| Service | Provider | Approx. Monthly Cost |
| --- | --- | --- |
| Compute — OCI VMs (karma, indra, monitoring) | Oracle Cloud | ₹0 (Free Tier) / ~$30 on paid |
| Serverless compute | Cloudflare Workers/Pages | ₹0 (Free Tier) |
| Frontend hosting (unnati) | Vercel | ₹0 (Hobby) / $20 Pro |
| Database + Auth | Supabase | $0 (Free) / $25 Pro |
| LLM Inference — Groq | Groq | $10–50 (usage-based) |
| LLM Inference — Anthropic | Anthropic API | $20–100 (usage-based) |
| LLM Inference — OpenAI | OpenAI | $10–30 (usage-based) |
| Terraform State | Terraform Cloud | $0 (Free) / $20 Plus |
| Domain + DNS | Cloudflare | ~$12/year |
| TOTAL (current) |  | ~$60–250/month depending on AI usage |

## 7.2  Target Monthly Spend (Post-Migration, Cloud VM Option)

| Service | Provider | Approx. Monthly Cost |
| --- | --- | --- |
| India VM — Application (4 vCPU, 16GB) | AWS ap-south-1 / Hetzner | ~$60–80 (~₹5,000–6,500) |
| India GPU VM — AI Inference (T4 16GB) | AWS g4dn.xlarge ap-south-1 | ~$30–60 (spot) / $130 on-demand |
| Cloudflare CDN + Workers | Cloudflare | $0–10 (mostly free tier) |
| LLM API fallback (complex tasks only) | Anthropic Claude API | $5–20 (80% reduction) |
| Domain + DNS | Cloudflare | ~$1/month |
| Supabase self-hosted | Included in India VM | $0 (self-managed) |
| Vercel | Removed | $0 |
| Terraform Cloud | Removed (MinIO state) | $0 |
| TOTAL (target, cloud VM) |  | ~$100–170/month — roughly similar cost, India-resident, 80%+ AI cost reduction |

## 7.3  Target Monthly Spend (Post-Migration, Home Server)

| Service | Provider | Approx. Monthly Cost |
| --- | --- | --- |
| Home server electricity (700W avg) | Local (Hyderabad DISCOM) | ~₹3,500–5,000/month |
| Internet — 200 Mbps business fiber | Airtel / Jio Business | ~₹3,000–5,000/month |
| UPS maintenance + consumables | Local | ~₹500/month amortised |
| Cloudflare CDN + Workers | Cloudflare | $0–10 |
| LLM API fallback only | Anthropic API | $5–10 |
| TOTAL (home server, after HW paid off) |  | ~₹7,000–10,500/month (~$85–125) — maximum control, lowest recurring cost |

# 8. Risks & Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Database migration data loss | Low | Critical | pg_dump/restore + checksums + 1-week dual-run + automated backups to separate India storage |
| Auth migration breaks existing sessions | Medium | High | Self-hosted Supabase uses same JWT format; matching JWT_SECRET avoids forced re-login |
| LLM quality regression (local vs. API) | Medium | Medium | A/B testing narad responses; keep API fallback; use quantised models only after benchmark |
| Home server power/connectivity outage | Medium (Hyderabad) | High | UPS + LTE failover + Cloudflare tunnel as backup; critical services replicated to small cloud VM |
| Supabase self-host maintenance overhead | Medium | Medium | Use official Supabase Docker Compose; enable auto-updates; monitor via Grafana |
| Terraform state migration failure | Low | Medium | Back up current Terraform Cloud state before migration; test in isolated workspace first |
| K3s node failure | Low | High | Multi-node K3s with at least 1 worker node; PVC data on durable storage (not ephemeral) |
| India data center regulatory change | Very Low | Low | Self-hosting gives direct control; no dependency on third-party data center policy changes |

# 9. Master Implementation Checklist

## Phase 1 — Foundation (Weeks 1–4)

- [ ] Provision India-resident VM (AWS ap-south-1 or Hetzner) — min 4 vCPU, 16GB RAM, 100GB SSD

- [ ] Run Znext vm-setup.sh on new India VM

- [ ] Configure Tailscale VPN — connect dev machine + India VM

- [ ] Set up Caddy/Nginx reverse proxy with SSL (Cloudflare origin certs)

- [ ] Migrate karma — stop OCI, rsync volumes, start on India VM, validate

- [ ] Migrate indra (n8n) — stop OCI, rsync Docker volumes, start on India VM, update webhooks

- [ ] Verify Prometheus + Grafana + Loki all operational on India VM

- [ ] Decommission karma and indra OCI VMs

## Phase 2 — Data Sovereignty (Weeks 5–10)

- [ ] Deploy self-hosted Supabase stack on India VM (docker-compose from supabase/supabase)

- [ ] Export hosted Supabase DB: pg_dump --format=custom --schema=app_data

- [ ] Restore to self-hosted Postgres: pg_restore

- [ ] Verify all tables, RLS policies, indexes, pgvector extension

- [ ] Update SUPABASE_URL + keys in: narad, vishwakarma, chitragupta, kanak, unnati

- [ ] Test auth flows: kanak login, unnati login/register, vishwakarma client provisioning

- [ ] Run 1-week dual-write validation — compare row counts and checksums daily

- [ ] Build and deploy unnati as Docker container on India VM behind Caddy

- [ ] Update DNS for unnati subdomain from Vercel to India VM

- [ ] Delete Vercel project after 1-week validation

- [ ] Migrate Terraform state from Terraform Cloud to MinIO on India VM

- [ ] Provision Vault or Infisical for secrets management — migrate .env injection

## Phase 3 — AI Sovereignty (Weeks 8–14)

- [ ] Provision GPU VM (AWS g4dn.xlarge ap-south-1 or dedicated GPU hardware)

- [ ] Install Ollama + CUDA drivers on GPU node

- [ ] Pull models: llama3.1:8b, mistral:7b, codellama:7b, nomic-embed-text

- [ ] Benchmark Ollama response quality vs. Groq for narad use cases

- [ ] Update narad LLM provider config: Ollama as primary, Groq/Anthropic as fallback

- [ ] Replace OpenAI embedding calls with Ollama nomic-embed-text

- [ ] Re-embed existing brain/knowledge graph entries with local model

- [ ] Monitor: inference latency, error rate, token throughput via Grafana

- [ ] (Optional) Evaluate RTX 4070 Ti home server for base inference load

- [ ] Reduce Groq/OpenAI/Anthropic API spend by routing 80%+ to local inference

# 10. Appendix — Current Platform Status Reference

The following table summarises the current Vishwakarma platform services as documented in the checkpoint file, for reference during migration planning.

| Service | Type | Status | Key Dependencies to Migrate |
| --- | --- | --- | --- |
| narad | CF Pages + React (AI Workspace) | ✅ Active | Supabase (brain), Groq/Anthropic (inference), Neo4j (graph) |
| vishwakarma | CF Workers (Cloud Provisioning) | ✅ Active | Supabase Auth, Terraform Cloud, GitHub Actions |
| chitragupta | CF Workers (Financial Data) | ✅ Active | Supabase (minimal), EdDSA auth self-managed |
| karma | Python FastAPI + Docker | ✅ Active | OCI VM → India VM migration (Phase 1) |
| kanak | CF Pages (Landing Page) | ✅ Active | Supabase Auth (Phase 2) — CF Pages retained |
| unnati | Next.js on Vercel | ✅ Active | Vercel → India VM Docker (Phase 2), Supabase Auth |
| indra | n8n Docker on OCI | ✅ Active | OCI VM → India VM migration (Phase 1) |

## Key Completed Milestones (Znext Plans)

- 01 — Karma Security: Phases 1–3 complete (AES-256, sandboxed execution, trust minimization)

- 03 — Vishwakarma Connect: SSH + Test Connection UI implemented

- 05 — Narad Connectors: Telegram, WhatsApp, Slack, Teams adapters complete

- 06 — Containerization: Docker/K3s provisioning on OCI VMs complete

- 07 — Metrics Stack: Prometheus + Grafana with service-level metrics complete

- 08 — Log Aggregation: Loki + Promtail centralised logging complete

- 09 — Knowledge Graph: Neo4j with entity extraction and recommendations complete

## Next Active Priority

| IMMEDIATE | Znext/02_vm-migration-plan.md — Provision OCI VM (or India VM as per this plan), transfer Work folder via SFTP, execute vm-setup.sh. This is the precursor step that enables all three phases of this migration plan. |
| --- | --- |

Vishwakarma Platform — India Self-Hosting Migration Plan Prepared by Deepak Chary ¦ April 2026 ¦ For internal strategic use only Making Vishwakarma truly swadeshi — compute, data, and intelligence, rooted in India.